# Tips for documenting the project plan

## Product: CAP (Code Analyzer Plugin)

## Roles

- Jean : Integrator, SVN guru

- David: Team leader, project planning/scheduling

- Quek: Group leader, Performance tuning expert

- Chris: Group leader, lookout for other tools, Issue management

- Ravi:  Testing expert, documentation expert

- Daud: Visual Studio guru, resharper expert

## Master plan

| Major milestones |  | V0.2 → |  |  | V0.3→ | V1.0beta→ |
| --- | --- | --- | --- | --- | --- | --- |
| Minor milestones |  | [Iteration C1] [1 week] V0.1.1→ | [Iteration C2][1 week] V0.1.2→ | [Iteration C3][1 week] | [2 weeks] | [3 weeks] |
| Front-end | Jean | Feature subset FE1 | Feature subset FE2 | Performance testing | -All front-end features | -Add optional features -Performance tuning |
|  | David |  |  |  |  |  |
|  | Quek |  |  |  |  |  |
| Back-end | Chris | Feature subset BE1 | Feature subset BE2 | Performance testing | -All back-end features | -Performance tuning |
|  | Ravi |  |  |  |  |  |
|  | Daud |  |  |  |  |  |

Notes:

Feature subset B1:

……

Feature subset F1:

….

## Detailed iteration plan

Plan for Iteration C1 [9/6/2007 – 16/6/2007] : V0.1.1

| Timeline |  | (3days) 12/06/2007→ |  | (2days) 14/06/2007→ | (2days) 16/06/2007→ | Total hrs |
| --- | --- | --- | --- | --- | --- | --- |
| Front-end | Jean | Parser for FE1a (6hrs) | Integrate parser and ADT (2hrs) | Parser for BOOL subset B1b (6hrs) | Integrate (4hrs) | 20 |
|  | David | ADT for FE1a (6hrs) |  | ADT for B1b (6hrs) |  | 20 |
|  | Quek | Class1, Class2 (18hrs) |  |  |  | 20 |
| Back-end | Chris | Parser for BE1a (15hrs) |  |  |  | 20 |
|  | Ravi | Evaluator for BE1a (18hrs) |  |  |  | 20 |
|  | Daud | Result calculator (5hrs) |  |  |  | 10 |

Other action items:

- Project meetings: Thurs 12-2 (2hrs)

- Chris → find a tool for line counting (3hrs)

- Daud → organize group programming session to demonstrate visual studio tips and tricks (also circulate a document on this) – 5hrs

- David → arrange meeting with supervisor to clarify doubts

- Daud can put in only 10hrs for the project for this iteration. He will make up for it by putting in 30hrs next iteration.

External functionality to be delivered:

V0.1.1 will be able to support features subsets FE1a and BE1a.

Internal functionality to be implemented:

Add more functionality to the parser,

Add Class3, Class4

…

## End-of-iteration analysis

Once the iteration is over, we do an end-of-iteration analysis. An example is given below:

- Additional meeting held on Fri 12-1

- Quek found a third party data structure suitable for relationship tables, and finished implementing all relationship tables. This means less implementation work in future.

- Chris could not find time to look for a line counting team; postponed for next iteration

- Jean could not finish BOOL subset B1a. parser takes more effort than expected. Need to adjust future project plan.